DarshanEase

Temple Darshan Ticket Booking System

Project Planning

Sprint Plan & Milestones

# 1. Product Backlog & Sprint Schedule

| Sprint | Functional Requirement (Epic) | User Story | Story Points | Duration |
| --- | --- | --- | --- | --- |
| Sprint 1 | Devotee Authentication | As a devotee, I can register and log in securely so I can access the platform | 8 | 2 Days |
| Sprint 1 | Temple & Darshan Browsing | As a devotee, I can view temples and their darshan slots with timings and pricing | 8 | 2 Days |
| Sprint 2 | Ticket Booking | As a devotee, I can book a normal or VIP darshan ticket and receive a QR e-ticket | 13 | 3 Days |
| Sprint 2 | Booking Management | As a devotee, I can view my booking history and cancel a booking | 5 | 1 Day |
| Sprint 3 | Organizer Temple Management | As an organizer, I can view and update my assigned temple's details | 8 | 2 Days |
| Sprint 3 | Organizer Darshan Management | As an organizer, I can create, update and delete darshan slots for my temple | 8 | 2 Days |
| Sprint 3 | Organizer Dashboard | As an organizer, I can view booking stats for my temple on a dashboard | 5 | 1 Day |
| Sprint 4 | Admin User/Organizer Management | As an admin, I can view, create, block and delete user and organizer accounts | 8 | 2 Days |
| Sprint 4 | Admin Temple Management | As an admin, I can create temples and assign organizers to them | 5 | 1 Day |
| Sprint 4 | Admin Dashboard | As an admin, I can view system-wide statistics on a dashboard | 5 | 1 Day |

# 2. Sprint Timeline

| Sprint | Start Date | End Date | Story Points | Sprint Release Date |
| --- | --- | --- | --- | --- |
| Sprint 1 | Day 1 | Day 4 | 16 | Day 4 |
| Sprint 2 | Day 5 | Day 8 | 18 | Day 8 |
| Sprint 3 | Day 9 | Day 12 | 21 | Day 12 |
| Sprint 4 | Day 13 | Day 16 | 18 | Day 16 |

# 3. Velocity

With an average team velocity of approximately 18 story points per 4-day sprint, the DarshanEase MVP (73 total story points across four sprints) was planned for completion within 16 working days, followed by integration testing, UAT and deployment.

# 4. Team Roles & Responsibilities

- Backend Developer(s): Own Sprint deliverables for models, controllers, routes, and authentication middleware

- Frontend Developer(s): Own Sprint deliverables for React pages, routing, and API integration per role

- QA/Tester: Executes UAT test cases at the end of each sprint and logs defects

- Project Lead: Tracks sprint burndown, unblocks the team, and coordinates final submission/deployment

# 5. Definition of Done

- Feature implemented on both backend (API + model + validation) and frontend (UI + API integration)

- Role-based access control verified for the feature

- Manually tested against the corresponding UAT test case

- No console/server errors during the happy path and key edge cases